## Sheet1
System Name: | Adopt-A-Pet
Members: | Abdullah, Anamerah M.
Dutosme, Jan Raye Edbert L.
Gales, Chrizza Arnie T.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September | [8 empty] | October | [31 empty] | November | [30 empty] | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | ... | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 1 | 2 | 3
1. User Registration and Authentication | Jan Raye Dutosme
1.1. Design UI/UX Figma | Jan Raye Dutosme | 2024-09-01 | 2024-09-03 | Done
1.2 Development of User Interface | Jan Raye Dutosme | 2024-09-30 | 2024-10-02 | Done
1.3. Integrate with DB | Jan Raye Dutosme | 2024-10-11 | 2024-10-23 | Done
1.4 Implement Data Validation | Jan Raye Dutosme | 2024-10-15 | 2024-10-21 | Done
1.5 Implement Security Measures | Jan Raye Dutosme | 2024-10-21 | 2024-10-05 | Done
1.6 Testing | Jan Raye Dutosme | 2024-10-26 | 2024-12-03 | Done
2. Profile Management | Anamerah Abdullah
2.1 Design UI/UX Figma | Anamerah Abdullah | 2024-09-01 | 2024-09-03 | Done
2.2 Development of User Interface | Anamerah Abdullah
2.2.1 UI for Adopter Dashboard | Anamerah Abdullah | 2024-10-25 | 2024-10-27 | Done
2.2.2 UI for Shelter Admin Dashboard | Anamerah Abdullah | 2024-10-26 | 2024-10-28 | Done
2.3 Implement Profile Update Logic | Anamerah Abdullah | 2024-10-27 | 2024-11-09 | Done
2.4 Integrate with Database | Anamerah Abdullah | 2024-10-27 | 2024-10-29 | Done
2.5 Develop Password Management Features | Anamerah Abdullah | 2024-10-29 | 2024-10-30 | Done
2.6 Implement Data Validation | Anamerah Abdullah | 2024-10-29 | 2024-11-12 | Done
2.7 Testing | Anamerah Abdullah | 2024-11-28 | 2024-12-03 | Done
3. Pet Listing | Anamerah Abdullah
3.1 Design UI/UX Figma | Anamerah Abdullah | 2024-09-01 | 2024-09-03 | Done
3.2 Development of UI for Adopter Dashboard | Anamerah Abdullah
3.2.1 Pet listing | Anamerah Abdullah | 2024-09-28 | 2024-10-18 | Done
3.2.2 View Pet Detail | Anamerah Abdullah | 2024-09-29 | 2024-10-19 | Done
3.3 Development of UI for Admin Dashboard | Anamerah Abdullah
3.3.1 Pet Management | Anamerah Abdullah | 2024-10-12 | 2024-10-17 | Done
3.3.2 View Pet Detail | Anamerah Abdullah | 2024-10-12 | 2024-10-18 | Done
3.3.3 Add Pet | Anamerah Abdullah | 2024-10-12 | 2024-11-08 | Done
3.3.4 Update Pet | Anamerah Abdullah | 2024-10-12 | 2024-11-12 | Done
3.3 Implement Pet Listing Logic for Adopter Dashboard | Anamerah Abdullah | 2024-09-30 | 2024-10-19 | Done
3.4 Implement Pet Management Logic for Admin Dashboard | Anamerah Abdullah | 2024-10-12 | 2024-10-20 | Done
3.5 Integrate with Database | Anamerah Abdullah | 2024-09-30 | 2024-10-26 | Done
3.6 Develop Pet Search | Anamerah Abdullah | 2024-10-13 | 2024-10-14 | Done
3.7 Develop Pet Filter | Anamerah Abdullah | 2024-10-13 | 2024-11-08 | Done
3.8 Implement Validations | Anamerah Abdullah | 2024-11-05 | 2024-11-12 | Done
3.9 Testing | Anamerah Abdullah | 2024-11-28 | 2024-12-03 | Done
4. Dashboard/Homepage | Anamerah Abdullah
2.1 Design UI/UX Figma | Anamerah Abdullah | 2024-09-01 | 2024-09-03 | Done
2.2 Development of User Interface | Anamerah Abdullah
2.2.1 UI for Adopter Dashboard | Anamerah Abdullah | 2024-11-09 | 2024-11-22 | Done
2.2.2 UI for Shelter Admin Dashboard | Anamerah Abdullah | 2024-11-08 | 2024-11-22 | Done
2.3 Implement Logic | Anamerah Abdullah | 2024-11-08 | 2024-11-22 | Done
2.4 Testing | Anamerah Abdullah | 2024-11-28 | 2024-12-03 | Done
5. Adoption Request | Chrizza Arnie Gales
5.1 Design UI/UX Figma | Chrizza Arnie Gales | 2024-09-01 | 2024-09-03 | Done
5.2 Adoption Request Form UI for Adopter Dashboard | Chrizza Arnie Gales | 2024-09-29 | 2024-09-30 | Done
5.2.1 Implement Request Submission Logic for Adopter Dashboard | Chrizza Arnie Gales | 2024-09-29 | 2024-10-26 | Done
5.3 Integrate with Database | Chrizza Arnie Gales | 2024-09-29 | 2024-10-26 | Done
5.4 Adoption Request UI for Admin Dashboard | Chrizza Arnie Gales | 2024-10-15 | 2024-11-30 | Done
5.4.1 Develop Admin Approval Workflow | Chrizza Arnie Gales | 2024-11-18 | 2024-11-30 | Done
5.4.2 Create Adopter Request Tracking System | Chrizza Arnie Gales | 2024-10-18 | 2024-11-27 | Done
5.5 Implement Data Form Validation | Chrizza Arnie Gales | 2024-10-14 | 2024-11-24 | Done
5.6 Testing | Chrizza Arnie Gales | 2024-10-15 | 2024-12-03 | Done
6. Pick-Up Schedule | Chrizza Arnie Gales
6.1 Design UI/UX Figma | Chrizza Arnie Gales | 2024-09-01 | 2024-09-03 | Done
6.2 Schedule Form UI for Adopter Dashboard | Chrizza Arnie Gales | 2024-10-12 | 2024-10-14 | Done
6.2.1 Implement Scheduling Logic for Adopter Dashboard | Chrizza Arnie Gales | 2024-10-12 | 2024-10-26 | Done
6.3 Integrate with Database | Chrizza Arnie Gales | 2024-10-12 | 2024-10-26 | Done
6.4 Pick-up Tracking UI for Admin Dashboard | Chrizza Arnie Gales | 2024-10-15 | 2024-11-30 | Done
6.4.1 Develop Pick-Up Status Tracking for Admin Dashboard | Chrizza Arnie Gales | 2024-10-15 | 2024-11-30 | Done
6.5 Testing | Chrizza Arnie Gales | 2024-11-28 | 2024-12-03 | Done
7. Notification | Jan Raye Dutosme / Anamerah Abdullah
7.1 Design UI/UX Figma | Anamerah Abdullah | 2024-09-01 | 2024-09-03 | Done
7.2 Development of User Interface | Jan Raye Dutosme / Anamerah Abdullah | 2024-10-29 | 2024-11-30 | Done
7.3 Develop Notification Logic | Jan Raye Dutosme / Anamerah Abdullah | 2024-09-30 | 2024-11-30 | Done
7.4 Integrate with Database | Jan Raye Dutosme / Anamerah Abdullah | 2024-09-29 | 2024-12-01 | Done
7.5 Implement Notification Preferences | Jan Raye Dutosme / Anamerah Abdullah | 2024-11-08 | 2024-12-01 | Done
7.6 Testing | Jan Raye Dutosme / Anamerah Abdullah | 2024-10-30 | 2024-12-03 | Done